## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status | Responsible Person
Project Planning & Scope Finalization | 2024-03-01 | 2024-03-15 | 15 | High | In Progress | Jane Doe
Market Research & Analysis | 2024-03-16 | 2024-04-05 | 21 | Middle | Pending | John Smith
Design Phase – UI/UX Development | 2024-04-06 | 2024-05-10 | 35 | High | Not Started | Lisa Chen
Development & Coding Implementation | 2024-05-11 | 2024-07-30 | 81 | High | Pending | <Marcus Lee
Testing & Quality Assurance | 2024-08-01 | 2024-08-25 | 25 | Middle | Not Started | <Sophia Kim
Client Review & Final Approval | 2024-08-26 | 2024-09-05 | 10 | High | Pending | Jane Doe
Time Management – Project Template (Client View)