## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status | Allocated Hours
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | High | Completed | 4
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | High | In Progress | 20
Design Phase Finalization | 2024-04-11 | 2024-04-18 | 8 | Medium | Not Started | 16
Development Start | 2024-04-19 | 2024-05-15 | 28 | High | Planned | 80
Testing & Quality Assurance | 2024-05-16 | 2024-05-31 | 16 | High | Not Started | 32
Final Review & Deployment | 2024-06-01 | 2024-06-05 | 5 | High | Not Started | 8