## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status | Responsible Person
Project Planning | 2024-03-01 | 2024-03-05 | 5 | High | In Progress | John Doe
Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 | High | On Track | Jane Smith
Design Phase | 2024-03-16 | 2024-03-31 | 16 | Medium | Not Started | Alex Johnson
Development Phase | 2024-04-01 | 2024-05-15 | 65 | High | In Progress | Team A
Testing & Quality Assurance | 2024-05-16 | 2024-06-10 | 35 | High | On Track | Sarah Lee
Deployment & Launch | 2024-06-11 | 2024-06-15 | 5 | Critical | Not Started | Mike Brown