## Worksheet
Task | Start Date | End Date | Duration (Days) | Assigned To | Priority | Status | Dependencies | Milestones | Notes
Project Initiation | 2023-10-01 | 2023-10-05 | 5 | John Doe | High | Completed |  | Initiation Complete | Finalize project scope and objectives.
Requirements Gathering | 2023-10-06 | 2023-10-18 | 13 | Jane Smith | High | In Progress | Task 1.2, Task 1.3 |  | Collect input from stakeholders and document functional requirements.
Design Phase | 2023-10-19 | 2023-11-05 | 18 | Alex Turner | Medium | Not Started | Task 2.1, Task 2.2 | Design Approved | Develop UI/UX mockups and technical architecture.
Development | 2023-11-06 | 2024-01-15 | 70 | Team A (Dev) | High | Not Started | Task 3.1, Task 3.2 |  | Build core features and integrate APIs.
Testing & QA | 2024-01-16 | 2024-02-05 | 20 | Sarah Lee | High | Not Started | Task 4.1, Task 4.2 |  | Conduct unit, integration, and user acceptance testing.
Deployment | 2024-02-06 | 2024-02-10 | 5 | Mike Wong | Medium | Not Started |  | Go-Live Date | Deploy application to production environment.
Post-Deployment Support | 2024-02-11 | 2024-03-31 | 61 | Support Team | Low | Not Started |  |  | Monitor performance, handle tickets, and provide training.