## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Allocated Time (hrs) | Status | Notes
Project Planning | 2024-04-01 | 2024-04-05 | 5 | High | 8 | In Progress | Define objectives, scope, and milestones.
Market Research | 2024-04-06 | 2024-04-15 | 10 | Medium | 12 | Not Started | Conduct surveys and competitor analysis.
Design Phase | 2024-04-16 | 2024-05-10 | 25 | High | 30 | Planned | Create wireframes and UI mockups.
Development | 2024-05-11 | 2024-07-30 | 80 | High | 80 | Not Started | Build core features and integrate APIs.
Testing & QA | 2024-08-01 | 2024-08-15 | 15 | High | 20 | Scheduled | Perform unit, integration, and user testing.
Deployment | 2024-08-16 | 2024-08-17 | 2 | Medium | 4 | Not Started | Release to production environment.