## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Allocated Hours | Status | Dependencies | Responsible Person | Notes
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | High | 10 | In Progress |  | Alice Johnson | Finalize project scope and stakeholders.
Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | High | 15 | Planned | Project Initiation | Bob Smith | Conduct interviews and document functional requirements.
Design Phase | 2024-04-16 | 2024-05-10 | 25 | Medium | 20 | Scheduled | Requirements Gathering | Charlie Brown | Develop wireframes and UI mockups.
Development Phase | 2024-05-11 | 2024-07-15 | 65 | High | 80 | Not Started |  | David Lee | Build core functionality and integrate modules.
Testing & QA | 2024-07-16 | 2024-08-10 | 35 | High | 30 | Scheduled | Development Phase | Eva Martinez | Perform unit, integration, and user acceptance testing.
Deployment | 2024-08-11 | 2024-08-15 | 5 | Critical | 8 | Planned |  | Frank Wilson | Go live on production environment with rollback plan.
Post-Launch Review | 2024-08-16 | 2024-08-18 | 3 | Low | 4 | Scheduled |  | Grace Taylor | Collect feedback and document lessons learned.