## Worksheet
Task | Start Date | End Date | Duration (Days) | Allocated Hours | Resource | Status | Budget (USD) | Progress (%)
Project Planning | 2024-03-01 | 2024-03-10 | 10 | 80 | Project Manager | Completed | 5,000 | 100%
Market Research | 2024-03-11 | 2024-03-25 | 15 | 90 | Research Analyst | In Progress | 7,500 | 65%
Design Development | 2024-03-26 | 2024-04-15 | 20 | 160 | UI/UX Designer | Pending Start | 12,000 | 0%
Development Phase | 2024-04-16 | 2024-05-31 | 46 | 380 | Developer Team | Not Started | 25,000 | 0%
Quality Assurance | 2024-06-01 | 2024-06-15 | 15 | 120 | QA Engineer | Scheduled | 8,000 | 0%
Launch & Review | 2024-06-16 | 2024-06-30 | 15 | 100 | Marketing Lead | Not Started | 6,000 | 0%