## Worksheet
Task | Start Date | End Date | Time Allocation (hrs) | Priority | Status
Project Planning | 2023-10-01 | 2023-10-05 | 8 | High | In Progress
Research & Analysis | 2023-10-06 | 2023-10-12 | 16 | High | Not Started
Design Phase | 2023-10-13 | 2023-10-18 | 12 | Medium | Planned
Development & Coding | 2023-10-19 | 2023-11-05 | 40 | High | In Progress
Testing & Debugging | 2023-11-06 | 2023-11-15 | 18 | High | Not Started
Final Review & Delivery | 2023-11-16 | 2023-11-20 | 8 | Low | Planned
Total Estimated Time: |  |  |  |  | 92 hours