## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Responsible Person | Status
Project Planning Phase | 2024-03-01 | 2024-03-15 | 15 | High | Project Manager | In Progress
Requirement Gathering | 2024-03-16 | 2024-04-05 | 21 | High | Business Analyst | Pending
Design & Prototyping | 2024-04-06 | 2024-05-10 | 35 | Medium | UI/UX Designer | Not Started
Development Phase | 2024-05-11 | 2024-08-31 | 132 | High | Software Engineers | Planned
Testing & Quality Assurance | 2024-09-01 | 2024-10-15 | 56 | High | QA Team | Not Started
Deployment & Training | 2024-10-16 | 2024-11-30 | 45 | Medium | Operations Lead | Pending