## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Responsible | Status
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | High | Project Manager | Completed
Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | High | Business Analyst | In Progress
Design Phase | 2024-04-16 | 2024-05-05 | 20 | Medium | UI/UX Designer | Planned
Development Phase | 2024-05-06 | 2024-06-30 | 65 | High | Software Developers | Not Started
Testing & Quality Assurance | 2024-07-01 | 2024-07-15 | 15 | High | QA Engineer | Planned
Deployment & Launch | 2024-07-16 | 2024-07-18 | 3 | Critical | Operations Lead | Not Started