## Worksheet
Task | Start Date | End Date | Duration (days) | Priority | Responsible Person | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | High | Project Manager | Completed
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | High | Business Analyst | In Progress
Design Phase (UI/UX) | 2024-04-11 | 2024-04-25 | 15 | Medium | UX Designer | Planned
Development Phase | 2024-04-26 | 2024-05-30 | 35 | High | Software Engineers | Not Started
Testing & Quality Assurance | 2024-06-01 | 2024-06-15 | 15 | High | QA Team | Planned
Project Review & Final Sign-off | 2024-06-16 | 2024-06-16 | 1 | High | Project Manager | Not Started