## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Responsible Person | Status
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | High | Project Manager | Completed
Requirements Gathering | 2024-03-16 | 2024-03-25 | 10 | High | Business Analyst | In Progress
Design Phase | 2024-03-26 | 2024-04-10 | 15 | Medium | UI/UX Designer | Planned
Development Phase | 2024-04-11 | 2024-05-30 | 50 | High | Development Team | Not Started
Testing & Quality Assurance | 2024-06-01 | 2024-06-15 | 15 | High | QA Engineer | Planned
Project Review & Delivery | 2024-06-16 | 2024-06-18 | 3 | High | Project Manager | Not Started