## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status | Responsible
Project Planning | 2024-03-01 | 2024-03-07 | 7 | High | Completed | Alex Johnson
Requirements Gathering | 2024-03-08 | 2024-03-15 | 8 | High | In Progress | Sara Lee
Design Phase | 2024-03-16 | 2024-03-25 | 10 | Medium | Pending | Mark Chen
Development Phase | 2024-03-26 | 2024-04-15 | 21 | High | Not Started | Team A - Dev Group
Testing & QA | 2024-04-16 | 2024-04-30 | 15 | High | Not Started | Linda Kim
Deployment | 2024-05-01 | 2024-05-03 | 3 | High | Not Started | IT Operations Team
Post-Deployment Review | 2024-05-04 | 2024-05-06 | 3 | Low | Not Started | Project Manager
Time Management – Project Summary View (Version 1.0)