## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Priority | Responsible | Progress (%)
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Completed | High | Project Manager | 100%
Requirement Gathering | 2024-04-02 | 2024-04-10 | 9 | In Progress | High | Business Analysts | 60%
Design Phase | 2024-04-11 | 2024-04-25 | 15 | Planned | Medium | UI/UX Team | 0%
Development Phase | 2024-04-26 | 2024-05-31 | 36 | Not Started | High | Developers | 0%
Testing & QA | 2024-06-01 | 2024-06-15 | 15 | Planned | High | QA Team | 0%
Deployment & Go-Live | 2024-06-16 | 2024-06-16 | 1 | Not Started | Critical | IT Operations | 0%
Total Tasks | [6 empty] | 6