## Worksheet
Task | Start Date | End Date | Duration (days) | Responsible Person | Status | Dependencies | Milestones
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | John Smith | Completed | None | Project Kickoff
Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | Sarah Lee | In Progress | Project Initiation | Requirement Finalized
Design Phase | 2024-04-16 | 2024-04-25 | 10 | Michael Chen | Not Started | Requirements Finalized | Design Approved
Development Phase | 2024-04-26 | 2024-05-15 | 20 | Team A (Dev) | Not Started | Design Approved | Beta Version Ready
Testing & QA | 2024-05-16 | 2024-05-31 | 16 | Lisa Wong | Not Started | Development Complete | Bug Fix Report Finalized
Deployment & Launch | 2024-06-01 | 2024-06-05 | 5 | David Kim | Not Started | Testing Complete | Live Go-Live Date
Post-Launch Review | 2024-06-06 | 2024-06-10 | 5 | Project Manager | Not Started | Launch Complete | Review Report Submitted