## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | John Smith | Completed
Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | Sarah Lee | In Progress
Design Phase | 2024-04-16 | 2024-04-25 | 10 | Mike Johnson | Not Started
Development Phase | 2024-04-26 | 2024-05-15 | 20 | Team A | Not Started
Testing & Quality Assurance | 2024-05-16 | 2024-05-31 | 16 | Lisa Wong | Not Started
Deployment & Launch | 2024-06-01 | 2024-06-05 | 5 | David Brown | Not Started