## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | John Smith | Completed | -
Feasibility Study | 2024-03-06 | 2024-03-15 | 10 | Lisa Chen | In Progress | Project Initiation
Requirements Gathering | 2024-03-16 | 2024-04-10 | 35 | Mark Davis | Planned | Feasibility Study
Design Phase | 2024-04-11 | 2024-05-15 | 45 | Sarah Lee | Not Started | Requirements Gathering
Development Phase | 2024-05-16 | 2024-07-31 | 77 | Team A (Dev) | Planned | Design Phase
Testing & QA | 2024-08-01 | 2024-08-31 | 31 | Rachel Kim | Not Started | Development Phase
Deployment & Launch | 2024-09-01 | 2024-09-15 | 15 | David Brown | Not Started | Testing & QA
Post-Launch Review | 2024-09-16 | 2024-09-30 | 15 | John Smith | Planned | Deployment & Launch