## Worksheet
Task | Start Date | End Date | Duration | Responsible Party | Status
Project Initiation | 01/03/2024 | 05/03/2024 | 15 days | Project Manager | Completed
Requirements Gathering | 06/03/2024 | 15/03/2024 | 10 days | Client Representative | In Progress
Design Phase | 16/03/2024 | 30/03/2024 | 15 days | UI/UX Team | Planned
Development Phase | 01/04/2024 | 30/05/2024 | 60 days | Development Team | Not Started
Testing & Quality Assurance | 01/06/2024 | 15/06/2024 | 15 days | QA Team | Scheduled
Deployment & Launch | 16/06/2024 | 20/06/2024 | 5 days | IT Operations | Not Started
Post-Launch Support | 21/06/2024 | 30/06/2024 | 10 days | Support Team | Planned