## Worksheet
Task | Start Date | End Date | Duration | Status | Responsible | Dependencies
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 day | Completed | Project Manager | -
Requirements Gathering | 2024-03-16 | 2024-03-25 | 10 days | In Progress | Business Analyst | Kickoff Meeting
Design Phase | 2024-03-26 | 2024-04-10 | 15 days | Not Started | UX Designer | Requirements Gathering
Development Start | 2024-04-11 | 2024-05-15 | 45 days | In Progress | Development Team | Design Phase
Testing & QA | 2024-05-16 | 2024-06-10 | 35 days | Not Started | QA Engineer | Development Start
Final Review & Sign-off | 2024-06-11 | 2024-06-15 | 5 days | Not Started | Project Manager | Testing & QA
Go-Live Deployment | 2024-06-16 | 2024-06-17 | 2 days | Not Started | DevOps Team | Final Review & Sign-off