## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | John Smith | Completed | -
Requirement Gathering | 2024-03-06 | 2024-03-15 | 10 | Sarah Lee | In Progress | Project Initiation
Design Phase | 2024-03-16 | 2024-03-25 | 10 | Mike Johnson | Planned | Requirement Gathering
Development Phase | 2024-03-26 | 2024-04-15 | 21 | Team A (Dev) | Not Started | Design Phase
Testing & QA | 2024-04-16 | 2024-04-30 | 15 | Lisa Wong | Not Started | Development Phase
Deployment & Launch | 2024-05-01 | 2024-05-03 | 3 | Admin Team | Not Started | Testing & QA