## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Priority | Milestones | Dependencies | Progress (%)
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | John Doe | Completed | High | Feasibility Study Approved | None | 100%
Requirements Gathering | 2024-03-06 | 2024-03-18 | 13 | Sarah Kim | In Progress | High | User Stories Finalized | Project Initiation | 65%
Design Phase | 2024-03-19 | 2024-04-05 | 17 | Mike Chen | Not Started | Medium | Wireframes Approved | Requirements Gathering | 0%
Development Phase | 2024-04-06 | 2024-05-31 | 57 | Team A (Dev) | Not Started | High | Phase 1 MVP Ready | Design Phase | 0%
Testing & Quality Assurance | 2024-06-01 | 2024-06-25 | 25 | Lisa Wong | Not Started | High | Bug Resolution Report Ready | Development Phase | 0%
User Training & Documentation | 2024-06-26 | 2024-07-10 | 15 | Julia Patel | Not Started | Medium | Training Sessions Scheduled | Testing & QA Completed | 0%
Go-Live & Deployment | 2024-07-11 | 2024-07-15 | 5 | David Lee | Not Started | High | System Live - Version 1.0 | User Training Completed | 0%
Post-Implementation Review | 2024-07-16 | 2024-07-20 | 5 | Project Manager | Not Started | Low | Review Report Submitted | Go-Live Completed | 0%