## Worksheet
Task | Start Date | End Date | Duration (days) | Responsible Person | Status | Priority
Project Initiation | 2024-04-01 | 2024-04-05 | 5 | Jane Smith | Completed | High
Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | John Doe | In Progress | High
Design Phase | 2024-04-16 | 2024-05-05 | 21 | Lisa Chen | Planned | Middle
Development Phase | 2024-05-06 | 2024-07-15 | 71 | Marcus Lee | Not Started | High
Testing & QA | 2024-07-16 | 2024-08-10 | 25 | Sarah Kim | Delayed | High
Deployment & Launch | 2024-08-11 | 2024-08-15 | 5 | Alex Brown | <Completed | Middle
Post-Launch Review | 2024-08-16 | 2024-08-20 | 5 | Jane Smith | In Progress | Low
Total Duration |  |  | 142 days | Project Status Summary |  | On Track (with minor delays)