## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Progress (%) | Owner
Project Planning | 2024-03-01 | 2024-03-10 | 10 | Completed | 100% | Sarah Lee
Requirement Gathering | 2024-03-11 | 2024-03-25 | 15 | In Progress | 60% | David Kim
Design Phase | 2024-03-26 | 2024-04-15 | 20 | Pending | 0% | Lisa Chen
Development | 2024-04-16 | 2024-05-31 | 46 | Not Started | 0% | James Rodriguez
Testing & QA | 2024-06-01 | 2024-06-20 | 20 | Pending | 0% | Anna Patel
Deployment | 2024-06-21 | 2024-06-30 | 10 | Not Started | 0% | Mark Taylor