## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies | Milestones | Priority
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Manager | Completed | - | Kickoff Complete | High
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Business Analysts | In Progress | Kickoff Meeting | Final Requirements Signed Off | High
Design Phase (UI/UX) | 2024-04-11 | 2024-04-25 | 15 | Design Team | Planned | Requirements Finalized | Wireframes Approved | Medium
Development Phase (Frontend) | 2024-04-26 | 2024-05-15 | 21 | Frontend Developers | Not Started | UI/UX Design Complete | - (Pending) | High
Development Phase (Backend) | 2024-05-16 | 2024-06-10 | 35 | Backend Developers | Not Started | Frontend Complete, API Ready | - (Pending) | High
Testing & Quality Assurance | 2024-06-11 | 2024-06-30 | 30 | QA Team | Not Started | Backend Complete, API Functional | Bug Report Summary Finalized | High
User Training & Documentation | 2024-07-01 | 2024-07-10 | 10 | Training Officer | Not Started | Testing Complete, System Ready | Training Materials Distributed | Medium
Project Launch & Go-Live | 2024-07-11 | 2024-07-11 | 1 | Project Manager, IT Team | Not Started | Training Complete, Final Review Done | System Go-Live Successful | High
Post-Launch Review & Feedback | 2024-07-12 | 2024-07-31 | 30 | Project Manager, Stakeholders | Not Started | Launch Successful, User Access Enabled | Feedback Summary Submitted | Low