## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Budget Allocation ($) | Status | Progress (%)
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | 15 | Project Manager | 15,000 | Completed | 100%
Resource Allocation & Procurement | 2024-03-16 | 2024-04-05 | 20 | Finance Director | 25,000 | In Progress | 75%
Development Phase (Phase 1) | 2024-04-06 | 2024-05-15 | 40 | Engineering Team | 75,000 | Not Started | 0%
Testing & Quality Assurance | 2024-05-16 | 2024-06-10 | 35 | QA Lead | 30,000 | Not Started | 0%
Final Review & Deployment | 2024-06-11 | 2024-07-05 | 35 | Project Manager & CTO | 20,000 | Not Started | 0%