## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Priority
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Completed | High
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | In Progress | High
Design Phase (Wireframes) | 2024-04-11 | 2024-04-18 | 8 | Planned | Medium
Development Start | 2024-04-19 | 2024-05-15 | 28 | Not Started | High
Testing & Quality Assurance | 2024-05-16 | 2024-05-31 | 16 | Planned | Medium
Client Review & Feedback | 2024-06-01 | 2024-06-05 | 5 | Not Started | High
Final Delivery & Handover | 2024-06-06 | 2024-06-07 | 2 | Not Started | Low
Freelancer Project Timeline – Time Management