## Worksheet
Task | Start Date | End Date | Responsible Person | Status | Progress (%)
Project Initiation & Planning | 2024-03-01 | 2024-03-15 | Sarah Johnson | Completed | 100%
Market Research & Analysis | 2024-03-16 | 2024-04-10 | Mike Chen | In Progress | 75%
Product Design & Prototyping | 2024-04-11 | 2024-05-30 | Lisa Martinez | Not Started | 0%
Development & Testing | 2024-06-01 | 2024-08-31 | David Kim | Planned | 0%
User Feedback & Iteration | 2024-09-01 | 2024-10-15 | Emma Wilson | Not Started | 0%
Launch & Post-Launch Support | 2024-10-16 | 2024-12-31 | Team Lead Office | Not Started | 0%