## Worksheet
Month | Project Phase | Key Milestones | Start Date | End Date | Responsible Person | Status
January | Project Initiation & Planning | Feasibility Study, Budget Drafting, Stakeholder Meeting | 2024-01-01 | 2024-01-31 | Alex Rivera | Completed
February | Requirement Gathering & Analysis | User Interviews, Needs Assessment, Document Finalization | 2024-02-01 | 2024-02-28 | Sophia Chen | In Progress
March | Design & Prototyping | Wireframing, UI/UX Design, Prototype Review | 2024-03-01 | 2024-03-31 | Jordan Lee | Planned
April | Development & Testing | Feature Development, QA Testing, Bug Fixing | 2024-04-01 | 2024-04-30 | Maria Garcia | Scheduled
May | Deployment & Training | System Launch, User Training Sessions, Feedback Collection | 2024-05-01 | 2024-05-31 | Daniel Kim | Pending Start
June | Monitoring & Evaluation | Performance Review, KPI Analysis, Optimization Plan | 2024-06-01 | 2024-06-30 | Linda Patel | Not Started