## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies
Project Initiation | 01/01/2024 | 01/05/2024 | 5 | Project Manager | Completed
Requirements Gathering | 01/06/2024 | 01/20/2024 | 15 | Business Analyst | In Progress | Project Initiation
Design Phase | 01/21/2024 | 02/15/2024 | 35 | UI/UX Designer | Planned | Requirements Gathering
Development Phase | 02/16/2024 | 04/30/2024 | 75 | Development Team | Not Started | Design Phase
Testing & Quality Assurance | 05/01/2024 | 05/25/2024 | 25 | QA Engineer | Not Started | Development Phase
Deployment & Go-Live | 05/26/2024 | 05/31/2024 | 6 | IT Operations | Not Started | Testing & Quality Assurance
Post-Implementation Review | 06/01/2024 | 06/05/2024 | 5 | Project Manager | Not Started | Deployment & Go-Live