## Worksheet
Task | Start Date | End Date | Duration | Responsible Person | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 day | Project Manager | Completed
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 days | Business Analyst | In Progress
Design Phase | 2024-04-11 | 2024-04-25 | 15 days | UI/UX Designer | Planned
Development Phase | 2024-04-26 | 2024-05-31 | 36 days | Software Engineer Team | Scheduled
Testing & QA | 2024-06-01 | 2024-06-15 | 15 days | QA Lead | Not Started
Deployment & Go-Live | 2024-06-16 | 2024-06-18 | 3 days | Operations Team | Planned
Post-Launch Review | 2024-06-19 | 2024-06-20 | 2 days | Project Manager | In Progress
Total Duration: 68 days