## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Priority
Project Planning | 2024-04-01 | 2024-04-05 | 5 | Planned | High
Requirement Gathering | 2024-04-06 | 2024-04-15 | 10 | In Progress | High
Design Phase | 2024-04-16 | 2024-05-05 | 21 | Not Started | Medium
Development | 2024-05-06 | 2024-06-30 | 66 | Not Started | High
Testing & Quality Assurance | 2024-07-01 | 2024-07-20 | 20 | Not Started | High
Deployment & Launch | 2024-07-21 | 2024-07-31 | 11 | Not Started | Medium
Post-Launch Review | 2024-08-01 | 2024-08-05 | 5 | Not Started | Low
Total Tasks: 7 |  |  |  |  | High Priority (4)