## Worksheet
Task | Start Date | End Date | Duration | Responsible Person | Status | Dependencies
Project Initiation | 2024-03-01 | 2024-03-05 | 5 days | John Doe | Completed
Requirements Gathering | 2024-03-06 | 2024-03-15 | 10 days | Jane Smith | In Progress | Project Initiation
Design Phase | 2024-03-16 | 2024-04-05 | 21 days | Alex Johnson | Not Started | Requirements Gathering
Development Phase | 2024-04-06 | 2024-05-31 | 57 days | Team A (Dev) | Not Started | Design Phase
Testing & QA | 2024-06-01 | 2024-06-25 | 25 days | Sarah Lee | Not Started | Development Phase
Deployment & Launch | 2024-06-26 | 2024-06-30 | 5 days | Mark Wilson | Not Started | Testing & QA
Post-Launch Review | 2024-07-01 | 2024-07-05 | 5 days | Project Manager | Not Started | Deployment & Launch