## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Initiation | 01/03/2024 | 05/03/2024 | 15 days | Project Manager | Completed
Scope Definition | 06/03/2024 | 10/03/2024 | 3 weeks | Business Analyst | In Progress
Resource Allocation | 11/03/2024 | 14/03/2024 | 4 days | HR Manager | Pending
Phase 1 Development | 15/03/2024 | 30/04/2024 | 56 days | Development Team | Not Started
Testing & QA | 01/05/2024 | 30/05/2024 | 30 days | QA Lead | Not Started
Final Review & Approval | 01/06/2024 | 05/06/2024 | 5 days | Project Sponsor | Not Started
Go-Live & Deployment | 06/06/2024 | 08/06/2024 | 3 days | IT Operations | Not Started
Post-Implementation Review | 09/06/2024 | 15/06/2024 | 7 days | Project Manager | Not Started