## Project Timeline Report
Project Timeline Report – Time Management
Task ID | Task Name | Start Date | End Date | Status | Responsible Person | Duration (Days) th>
T-001 | Project Initiation Phase | 2024-03-15 | 2024-03-25 | Completed | Alice Johnson | 11
T-002 | Scope Definition & Stakeholder Meeting | 2024-03-26 | 2024-04-01 | In Progress | Bob Smith | 5
T-003 | Risk Assessment & Mitigation Planning | 2024-04-02 | 2024-04-10 | Pending Approval | Carol Davis | 9
T-004 | Resource Allocation & Team Setup | 2024-04-11 | 2024-04-18 | Scheduled | Dave Wilson | 8
T-005 | Phase 1 Development Start | 2024-04-19 | 2024-05-15 | Not Started | Eva Martinez | 37
T-006 | Testing & Quality Assurance Review | 2024-05-16 | 2024-06-10 | Pending Start | Fred Brown | 45
T-007 | Final Review & Deployment Planning | 2024-06-11 | 2024-06-30 | Not Started | Gina Lee | 20