## Worksheet
Task | Start Date | End Date | Status | Responsible Person
Project Initiation | 2024-03-01 | 2024-03-05 | Completed | Sarah Johnson
Requirement Gathering | 2024-03-06 | 2024-03-15 | In Progress | Marcus Lee
Design Phase | 2024-03-16 | 2024-03-31 | Pending | Lisa Chen
Development Phase | 2024-04-01 | 2024-05-15 | Not Started | David Kim
Testing & Quality Review | 2024-05-16 | 2024-06-10 | Not Started | Jennifer Torres
Deployment & Go-Live | 2024-06-11 | 2024-06-15 | Not Started | Alex Morgan
Post-Launch Review | 2024-06-16 | 2024-06-20 | Not Started | Sarah Johnson