## Worksheet
Task | Start Date | End Date | Responsible | Status
Project Initiation | 2024-03-01 | 2024-03-05 | John Doe | Completed
Market Research | 2024-03-06 | 2024-03-15 | Sarah Lee | In Progress
Product Design | 2024-03-16 | 2024-04-10 | Mike Chen | Not Started
Development Phase | 2024-04-11 | 2024-05-30 | Team A | Not Started
Testing & Quality Assurance | 2024-06-01 | 2024-06-15 | Lisa Kim | Planned
Launch & Marketing Campaign | 2024-06-16 | 2024-07-10 | Alex Wong | Not Started