## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status | Priority
Market Research & Analysis | 2024-03-15 | 2024-03-25 | 10 | Marketing Team | In Progress | High
Product Vision Finalization | 2024-03-26 | 2024-04-01 | 6 | CEO & Founder | Done | Critical
UI/UX Wireframing | 2024-04-02 | 2024-04-15 | 14 | Design Team | Planned | High
Development Sprint 1 | 2024-04-16 | 2024-05-03 | 18 | Engineering Team | In Progress | High
Beta Testing & Feedback Loop | 2024-05-04 | 2024-05-18 | 15 | Product Manager & QA | Planned | Medium
Launch Preparation (Marketing, PR) | 2024-05-19 | 2024-06-01 | 13 | Marketing & PR Team | Scheduled | High
Post-Launch Review & Iteration Plan | 2024-06-02 | 2024-06-15 | 14 | Product & Engineering Teams | Planned | Medium