## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies
Project Kickoff Meeting | Team Lead | 2024-04-01 | 2024-04-01 | 1 | Completed | None
Scope Definition & Stakeholder Alignment | Project Manager | 2024-04-02 | 2024-04-05 | 4 | In Progress | Kickoff Meeting
Requirements Gathering Workshop | UX Team | 2024-04-06 | 2024-04-10 | 5 | Planned | Scope Definition
Design & Wireframing Phase | Design Team | 2024-04-11 | 2024-04-18 | 8 | Planned | Requirements Workshop
Development Sprints (Phase 1) | Engineering Team | 2024-04-19 | 2024-05-03 | 15 | In Progress | Design & Wireframing
Testing & Bug Resolution | QA Team | 2024-05-04 | 2024-05-17 | 14 | Planned | Development Sprints
User Acceptance Testing (UAT) | Stakeholders | 2024-05-18 | 2024-05-25 | 8 | Planned | Testing & Bug Resolution
Project Final Review & Handover | Team Lead | 2024-05-26 | 2024-05-26 | 1 | Not Started | UAT Completion