## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status | Dependencies
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Manager | Completed
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | Business Analyst | In Progress | Project Kickoff Meeting
Design Phase | 2024-04-11 | 2024-04-25 | 15 | UI/UX Designer | Planned | Requirements Gathering
Development Phase | 2024-04-26 | 2024-05-30 | 35 | Development Team | Not Started | Design Phase
Testing & Quality Assurance | 2024-06-01 | 2024-06-15 | 15 | QA Lead | Not Started | Development Phase
User Training & Onboarding | 2024-06-16 | 2024-06-20 | 5 | Training Specialist | Not Started | Testing & QA
Project Review & Closure | 2024-06-21 | 2024-06-21 | 1 | Project Manager | Not Started | User Training & Onboarding
Template Version ¦ Purpose: Time Management ¦ Template Type: Project Timeline