## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible Person | Progress (%)
Project Initiation | 2024-03-01 | 2024-03-05 | 5 | Completed | Alice Smith | 100%
Requirement Gathering | 2024-03-06 | 2024-03-15 | 10 | In Progress | Bob Johnson | 65%
Design Phase | 2024-03-16 | 2024-03-25 | 10 | Planned | Carol Davis | 0%
Development Phase | 2024-03-26 | 2024-04-15 | 21 | Not Started | David Lee | 0%
Testing & QA | 2024-04-16 | 2024-04-30 | 15 | Planned | Eva Brown | 0%
Deployment & Go-Live | 2024-05-01 | 2024-05-03 | 3 | Not Started | Frank Wilson | 0%