## Worksheet
Week | Project Phase | Start Date | End Date | Key Tasks th> | Responsible Person | Status
Week 1 | Project Kickoff & Planning | 2024-04-01 | 2024-04-07 | Define objectives, scope, and deliverables Finalize project team assignments | Sarah Johnson | On Track
Week 2 | Requirements Gathering | 2024-04-08 | 2024-04-14 | Conduct stakeholder interviews Document functional and technical requirements | Mike Chen | On Track
Week 3 | Design & Prototyping | 2024-04-15 | 2024-04-21 | Create wireframes and UI mockups Review with stakeholders for feedback | Lisa Park | On Track
Week 4 | Development Start | 2024-04-22 | 2024-04-28 | Begin backend development Set up core database structure | David Ross | On Track
Week 5 | Development & Testing | 2024-04-29 | 2024-05-05 | Develop frontend features Run unit and integration tests | Team A/B | On Track
Week 6 | User Acceptance Testing (UAT) | 2024-05-06 | 2024-05-12 | Conduct UAT with end-users Collect feedback and resolve issues | Sarah Johnson | On Track
Week 7 | Final Review & Deployment | 2024-05-13 | 2024-05-19 | Final documentation Deploy to production environment | Operations Team | On Track