## Worksheet
Task | Project | Start Date | End Date | Estimated Time (hrs) | Actual Time (hrs) | Priority | Status | Assigned To | Dependencies
Requirement AnalysisMobile App Development2023-10-012023-10-104035HighCompletedSarah JohnsonN/A
UI/UX DesignMobile App Development2023-10-112023-10-256058HighIn ProgressAlex ChenRequirement Analysis
Backend DevelopmentMobile App Development2023-10-262023-11-1512095CriticalPlannedDavid KimUI/UX Design, API Prototyping
Frontend DevelopmentMobile App Development2023-11-162023-12-058070HighIn ProgressLisa PatelBackend Development, API Docs
Testing & QAMobile App Development2023-12-062023-12-205048HighScheduledJames WilsonBackend & Frontend Complete
Total Estimated Hours:350306