## Worksheet
Task | Project | Start Date | End Date | Allocated Time (hrs) | Priority | Status | Responsible Person
Requirements Gathering | New Customer Portal | 2024-03-15 | 2024-03-25 | 16 | High | In Progress | Sarah Johnson
UI/UX Design Phase | New Customer Portal | 2024-03-26 | 2024-04-10 | 18 | High | Planned | Mike Chen
Frontend Development | New Customer Portal | 2024-04-11 | 2024-05-15 | 36 | Medium | Not Started | Alex Rivera
Backend Integration | New Customer Portal | 2024-05-16 | 2024-06-10 | 30 | High | In Progress | David Kim
Testing & Quality Assurance | New Customer Portal | 2024-06-11 | 2024-06-30 | 14 | Medium | Not Started | Lisa Torres
Final Deployment & Training | New Customer Portal | 2024-07-01 | 2024-07-15 | 8 | Low | Planned | Rachel Patel