## Worksheet
Task | Start Date | End Date | Status | Priority | Estimated Hours th> | Actual Hours th>
Project Planning Meeting | 2023-10-03 | 2023-10-03 | Completed | High | 4 | 4.5
Design Wireframes | 2023-10-04 | 2023-10-10 | In Progress | Medium | 8 | 5
Develop Backend API | 2023-10-11 | 2023-10-25 | Pending | High | 20 | 0
User Testing Phase | 2023-11-01 | 2023-11-15 | Not Started | Medium | 6 | 0
Final Deployment & Review | 2023-11-20 | 2023-11-25 | Not Started | High | 5 | 0