## Worksheet
Project Name | Start Date | End Date | Current Phase | Daily Time Allocation (hrs) | Remaining Time (days) | Progress (%) | Next Action
Website Redesign | 2024-03-15 | 2024-05-30 | Design & Wireframes | 4 | 65 | 42% | Finalize UI mockups by April 10
Mobile App Development | 2024-04-01 | 2024-07-15 | Backend Setup | 6 | 110 | 28% | Complete API integration by April 25
Marketing Campaign Launch | 2024-03-20 | 2024-06-15 | Content Creation | 3 | 85 | 60% | Publish social media by May 10
Client Onboarding Process | 2024-03-10 | 2024-05-31 | Documentation Phase | 2 | 45 | 75% | Review onboarding checklist by April 15