## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status | Responsible Person | Estimated Hours | Actual Hours
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | High | Completed | Alice Johnson | 2 | 2
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 | High | In Progress | Bob Smith | 15 | 8
Design Phase | 2024-04-11 | 2024-04-25 | 15 | Medium | Not Started | Charlie Lee | 30 | 0
Development Phase | 2024-04-26 | 2024-05-31 | 36 | High | Not Started | David Brown | 80 | 0
Testing & QA | 2024-06-01 | 2024-06-15 | 15 | High | Not Started | Eva White | 20 | 0
Final Review & Deployment | 2024-06-16 | 2024-06-18 | 3 | High | Not Started | Frank Taylor | 6 | 0