## Worksheet
Task ID | Project Name | Task Title | Start Date | End Date | Duration (Days) | Priority Level | Assigned To | Status | Progress (%) | Time Block 1 (HH:MM) | Time Block 2 (HH:MM) | Time Block 3 (HH:MM) | Daily Focus Time (hrs) | Breaks & Buffer | Dependencies | Milestones | Notes
T-001 | Website Redesign Project | Design Phase Kickoff Meeting | 2024-04-01 | 2024-04-03 | 3 | High | Sarah Johnson | In Progress | 60% | 09:00 - 10:30 | 14:00 - 15:30 | 16:30 - 17:30 | 4.5 | 2 hours (lunch + 30-min buffer) | T-002, T-003 | Design Approval (Day 3) | Finalize wireframes and stakeholder feedback.
T-002 | Website Redesign Project | UI/UX Wireframe Development | 2024-04-04 | 2024-04-10 | 7 | High | Mark Davis | Planned | 0% | 09:00 - 11:30 | 13:30 - 15:30 | 16:00 - 17:30 | 5.5 | 1 hour (review session) | T-001, T-004 | Finalize user flow and navigation.
T-003 | Website Redesign Project | Client Review Session | 2024-04-11 | 2024-04-11 | 1 | Critical | Lisa Chen | Scheduled | 100% | 10:00 - 12:00 |  |  | 2 | None (live meeting) | T-002 | Final approval for wireframes.
T-004 | Website Redesign Project | Frontend Development Setup | 2024-04-12 | 2024-04-15 | 4 | Medium | Alex Turner | Not Started | 0% | 09:00 - 12:30 | 14:30 - 16:30 |  | 5.5 | 1 hour (code review) | T-002, T-003 | Configure development environment and tools.