## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status | Responsible Person | Notes
Project Planning | 2024-04-01 | 2024-04-05 | 5 | High | In Progress | John Doe | Finalize scope and timeline.
Design Phase | 2024-04-06 | 2024-04-15 | 10 | Medium | Not Started | Jane Smith | Create wireframes and UI mockups.
Development | 2024-04-16 | 2024-05-15 | 30 | High | Not Started | Alex Johnson | Build frontend and backend systems.
Testing & QA | 2024-05-16 | 2024-05-30 | 15 | High | Not Started | Sara Lee | Run comprehensive test cases and bug fixes.
Deployment | 2024-06-01 | 2024-06-03 | 3 | Medium | Not Started | Mike Brown | Deploy to production environment.