## Worksheet
Project Name | Start Date | End Date | Status | Priority | Assigned To | Daily Time Blocks | Total Estimated Hours | Progress % | Next Review Date
Website Redesign | 2024-03-01 | 2024-05-30 | In Progress | High | Sarah Johnson | 9:00–17:00 (8 hrs) | 160 | 65% | 2024-04-15
Mobile App Development | 2024-03-15 | 2024-07-31 | Planning | Critical | David Lee | 10:00–18:00 (8 hrs) | 240 | 25% | 2024-04-30
Client Onboarding Process | 2024-03-20 | 2024-04-15 | Completed | Medium | Lisa Chen | 9:00–16:00 (7 hrs) | 80 | 100% | 2024-05-15
Marketing Campaign Launch | 2024-04-01 | 2024-06-30 | Pending Approval | High | Mark Thompson | 10:30–17:30 (7 hrs) | 120 | 40% | 2024-05-25