## Worksheet
Task | Start Date | End Date | Duration (Days) | Priority | Status | Notes
Project Planning | 2024-04-01 | 2024-04-05 | 5 | High | In Progress | Finalize scope, assign roles.
Market Research | 2024-04-06 | 2024-04-15 | 10 | Medium | Not Started | Survey participants, analyze trends.
Design Phase | 2024-04-16 | 2024-05-03 | 19 | High | Planned | Wireframes, UI mockups.
Development | 2024-05-04 | 2024-06-15 | 43 | High | Scheduled | Frontend and backend coding.
Testing & QA | 2024-06-16 | 2024-07-05 | 21 | Medium | Not Started | Bug fixes, user acceptance.
Launch & Review | 2024-07-06 | 2024-07-15 | 11 | Low | Planned | Public release, gather feedback.